# 364 Lake Shore Drive — Excavation / Sitework Estimate Comparison (H-02)

RSBM vs. Bucket Enterprises, with Site Masters (received Friday 10/30/2026). Prepared 11/1/2026 from the estimate PDFs and emails. Nothing awarded, nothing sent.

# 1. Estimates received

| Vendor | Estimate | Date | Total | Valid until | Status / filing |
| --- | --- | --- | --- | --- | --- |
| RSBM Excavating (GBA Team LLC) | Sitework Proposal | 10/12/2026 | $90,000.00 | Not stated | Filed in H-02/RSBM. Unsigned (client and S. Holtzer lines blank). |
| Bucket Enterprises LLC | Est #1492 | 10/26/2026 | $143,663.00 | 11/26/2026 | Filed in H-02/Bucket. Asks to sign and return; ack sent 10/26. |
| Site Masters | Est #3994 | 10/30/2026 | NOT READ — PDF is an attachment I could not open | Unknown | Paving and flat work only (per email). PDF not found in SharePoint. See section 4. |

# 2. Line-by-line: RSBM vs. Bucket (comparable scope)

RSBM groups its pricing into 10 lines; Bucket prices 24. Bucket lines were mapped to the nearest RSBM line.

| Scope item | RSBM | Bucket | Notes |
| --- | --- | --- | --- |
| Erosion control (construction entrance, silt fence) | $4,100 | $4,710 | Bucket: entrance $1,800 (1 load stone) + silt fence $2,910. RSBM: any added measures billed separately. |
| Demolition of existing house | $4,900 | $6,500 | Both exclude dumpsters (Bucket: dumpsters by GC). RSBM includes water/sewer lateral disconnection. |
| Building excavation and backfill | $11,400 | $16,670 | Bucket = topsoil strip $1,820 + excavate $10,350 + backfill/rough grade $4,500. RSBM excludes topsoil strip and export. |
| Slab prep and rigid insulation | $8,900 | $9,325 | RSBM: 2" rigid + 4" crushed gravel. Bucket: 4" gravel $4,225 + rigid foam $5,100 (thickness not stated). |
| Site drainage + leader drains | $26,200 | $30,746 | RSBM: structures/12" HDPE $19,800 + leaders $6,400 (160 LF HDPE, 1 catch basin, 1,300 gal drywell). Bucket adds a dry swale. |
| Water service (4" DIP, wet tap) | $21,300 | $21,345 | Essentially equal. Bucket includes road restoration and traffic control; RSBM says paving restoration "as needed". |
| Sanitary sewer lateral (6") | $7,700 | $13,175 | RSBM: 60 LF SDR35, cleanout, tie-in. Bucket includes road restoration and traffic control. Largest unexplained gap. |
| Gas trench | $1,900 | $3,000 | Bucket includes electric trench and conduit. RSBM excludes electric trenching. |
| Fine grading | $3,600 | not listed | Bucket prices rough grading only. |
| Subtotal, comparable scope | $90,000 | $105,471 | Bucket is $15,471 higher on the same scope (17%). |

# 3. Bucket-only items (paving and flat work) — not in RSBM

| Item | Qty | Unit | Total |
| --- | --- | --- | --- |
| Concrete curb | 70 | $38.00 | $2,660 |
| 4" concrete sidewalk, patio, garbage pads | 1,186 | $16.00 | $18,976 |
| Parking lot: 4" item 4 subbase + 3" asphalt binder | 1,426 | $6.00 | $8,556 |
| Line striping and marking | 1 | $1,500 | $1,500 |
| Road widening: 12" subbase, 4" binder, 2" top course | 500 | $13.00 | $6,500 |
| Total paving / flat work |  |  | $38,192 |

Bucket total check: $105,471 + $38,192 = $143,663. This is the scope Site Masters Est #3994 appears to cover, so Site Masters is the cleaner comparison for this block.

# 4. Site Masters — Friday 10/30 information

Estimate #3994, dated 10/30/2026, received 10/30 at 12:21 PM ET from quotes@sitemastersny.com, sent to estimating@ and Abe, cc Chaim, Sol, Simon K. and the office.

Addressed to "Ohfalo", Site Masters, P.O. Box 532, Highland Mills NY 10930; phone 845-250-8010 (estimator Yidel Herskovitz, ext. 204).

Email body says only "See Attached Paving And Flat Work Measurements." No total in the body.

Two attachments: Est_3994_from_Site_Masters_23948.pdf (293 KB) and Paving And Flat Work.pdf (583 KB, measurements).

History: asked for files 10/12; full CD set sent 10/13; excavation follow-up sent 10/26; asked for our company info for QuickBooks 10/27 (sent 10/27).

GAP: the amount and line items are in the PDF, which I could not open. The estimate is paving/flat work only. No excavation, foundation excavation, utilities or drainage price has come from Site Masters, so it is not yet a full RSBM/Bucket alternative.

# 5. What is missing from RSBM

PAVING AND FLAT WORK: no curb, sidewalk/patio/garbage pads, parking-lot paving, striping or road widening ($38,192 in Bucket). Need confirmation these are out of RSBM scope, or a separate price.

ELECTRIC TRENCH / CONDUIT: gas trench only. Bucket includes electric and conduit.

TOPSOIL STRIP AND EXPORT, CLEARING AND GRUBBING: all excluded. Bucket prices the topsoil strip ($1,820) but also charges $375 per load for excess fill export.

IMPORT/EXPORT OF EXCESS MATERIAL: excluded, no rate given. Could be a large add depending on cut/fill.

ROAD RESTORATION AND TRAFFIC CONTROL: not priced (RSBM says "paving restoration as needed"). Bucket includes both on water and sewer.

DRY SWALE: in Bucket, not mentioned by RSBM. Confirm it is on the plan.

TREE REMOVAL: not in either (Bucket: "by others"). Fruit trees are a separate budget line.

OPEN-ENDED EXTRAS: jackhammering $2,600/day, dewatering $300/day, water-main-break repair up to $2,400, removal of existing underground utilities. No allowances in the $90,000.

SURVEY/STAKEOUT AND THIRD-PARTY TESTING: excluded (Bucket also excludes).

PLAN REFERENCE: proposal does not cite the engineer drawing (Bucket cites Friedlander Engineering 8.14.26). Ask RSBM to confirm which plan set and revision it priced, and confirm the 3,742 SF building area.

VALIDITY PERIOD AND SIGNATURES: no "valid until" date; unsigned. Payment is 25% on start of each job, then weekly progress billing.

FINE GRADING DIFFERENCE: RSBM includes $3,600; Bucket lists rough grading only. Even out when leveling.

# 6. Other open items on our side

Read Site Masters Est #3994 and its measurements PDF, enter the amount in the Bid Comparison tab, and file the PDF under H-02/Site Masters (currently not in SharePoint).

Ask Site Masters whether they will price excavation, drainage and utilities, not only paving.

Check the Bid Comparison tab shows RSBM $90,000 and Bucket $143,663 with working links (I did not open the workbook).

Security logs show RSBM crew (Pablo, Javier, David) entering the property "for work" through 10/30 although no signed RSBM proposal is on file. Worth confirming what they are doing.